## Security Status
ID | Category | Priority | Status | Title | Notes | Your action
SEC-001 | Security | P0 | Done | Admin auth + role gate on all admin routes | middleware.ts validates session + role=admin
SEC-005 | Security | P1 | Done | Blob URL allow-list is hostname-based | new URL().hostname check
SEC-006 | Security | P1 | Done | Impersonation step-up + notify + audit | Admin re-enters password; customer emailed; audited | Optional: IMPERSONATE_NOTIFY_CUSTOMER=false
SEC-008 | Security | P1 | Done | Invitation token consumption cap (max 10) | + migration | Run 2026-07-23-invitation-token-consumption-cap.sql
SEC-009 | Security | P1 | Done | Email template injection fixed | Single-pass + HTML-escape renderer; 7/7 tests
SEC-010 | Security | P1 | Done | Security headers | 5 enforced; CSP report-only | Flip CSP to enforcing after console check
SEC-012 | Security | P2 | Done | Don't leak internal errors | Public routes fixed; admin-detail accepted (documented)
SEC-013 | Security | P2 | Done | UUID validation before .or() (deal+lead) | Guards string-interpolated filters
SEC-014 | Security | P2 | Done | Removed verbose ID logging | task-responses diagnostics removed
SEC-016 | Security | P2 | Done | Secret-scanning CI (gitleaks) |  | .github workflow — enable Actions on GitHub
SEC-017 | Security | P2 | Done | Explicit CORS-deny on webhooks | Server-to-server only
SEC-019 | Security | P2 | Done | Dependabot config |  | .github/dependabot.yml — enable on GitHub
SEC-020 | Security | P2 | Done | server-only guard on supabaseAdmin | Throws if loaded in browser
SEC-022 | Security | P2 | Done | Recipient emails masked in logs | + PII subject dropped
SEC-024 | Security | P2 | Done | Upload token 2-min TTL | validUntil added
SEC-025 | Security | P2 | Done | backfill-shared-tasks behind admin gate | via middleware
SEC-026 | Security | P2 | Done | audit_logs table + recordAudit | + migration; wired impersonate/deletes | Run 2026-07-23-audit-logs.sql
SEC-027 | Security | P2 | Done | Key-rotation runbook | docs/key-rotation.md
SEC-028 | Security | P2 | Done | CI workflow (lint/typecheck/build/audit) |  | .github workflow — enable Actions on GitHub
CMP-002 | Compliance | P0 | Done | Consent capture at intake | Checkbox + version + timestamp (portal) | Run privacy-consent migration; set Privacy Policy URL
CMP-004 | Compliance | P1 | Done | Audit log of sensitive access (=SEC-026) | audit_logs + recordAudit | Run audit_logs migration
CMP-005 | Compliance | P2 | Done | Right-to-be-forgotten erase endpoint | POST /api/admin/leads/[id]/erase (audited) | Retention schedule/purge still to define
CMP-007 | Compliance | P1 | Done | Security headers (=SEC-010) | See SEC-010
CMP-008 | Compliance | P2 | Done | PII/errors in responses+logs (=SEC-012) | See SEC-012
GAP-003 | Gaps | P2 | Done | Backfill idempotency guard | migration_runs table | Run 2026-07-23-migration-runs.sql
GAP-004 | Gaps | P2 | Done | Shared-task mirror dedupe on retry | Code-level (multi-file safe)
GAP-005 | Gaps | P1 | Done | Deal delete is soft delete | No orphaned rows
GAP-006 | Gaps | P2 | Done | Deal status state machine | Closed is terminal
GAP-007 | Gaps | P1 | Done | Task status recalcs milestones
GAP-008 | Gaps | P1 | Done | Compensating del() on DB-insert failure | No orphan blobs; both repos
GAP-009 | Gaps | P2 | Done | Upload count/size/MIME limits | 25MB cap + type allow-list; both repos
GAP-010 | Gaps | P1 | Done | APS replacement side-scoped | No family-wide wipe
GAP-011 | Gaps | P2 | Done | Welcome email idempotency | Atomic claim before send; reverts on fail
GAP-013 | Gaps | P2 | Done | HTML-entity brace decoding | Decimal/hex/named in all 3 email helpers
GAP-014 | Gaps | P2 | Done | Milestone-email failures logged | Thrown + non-2xx, with IDs
GAP-016 | Gaps | P2 | Done | Lead email format validation | Duplicates intentionally allowed
GAP-017 | Gaps | P2 | Done | file_number format on deal edit | Single shared regex import+edit
GAP-018 | Gaps | P2 | Done | field_type enum check | Allow-list on task responses
GAP-019 | Gaps | P2 | Done | APS side auto-detect legacy rows | Reads custom_type for side
GAP-020 | Gaps | P1 | Done | activateClientDeals OR filter fix
GAP-021 | Gaps | P2 | Done | Zero-task milestone handling | Resolved by design (keeps manual status)
ARC-004 | Architecture | P2 | Done | Removed duplicate route stubs | Legacy URLs via next.config redirects
ARC-005 | Architecture | P2 | Done | Central dealMapper (toDeal) | Used by list + detail
ARC-008 | Architecture | P2 | Done | Global error boundary | error.tsx + global-error.tsx
ARC-010 | Architecture | P2 | Done | CLAUDE.md architecture brief | Authored
ARC-011 | Architecture | P2 | Done | Structured logger (LOG_LEVEL) | Adopted in session code | Optionally set LOG_LEVEL=warn in prod
SEC-002 | Security | P0 | In progress | Webhook HMAC signatures | Admin verifies + portal signs; per-endpoint enforcement added | Set SERVICE_WEBHOOK_SECRET in both; then SERVICE_WEBHOOK_ENFORCE_ROUTES=activate-deal
SEC-003 | Security | P0 | In progress | Private document storage | Code done both repos; dormant behind flag | Provision private-capable Blob store, then flip NEXT_PUBLIC_PRIVATE_BLOB
CMP-001 | Compliance | P0 | In progress | Gov IDs on public storage (=SEC-003) | See SEC-003 | See SEC-003
SEC-004 | Security | P1 | Deferred | Per-deal ownership (IDOR) | 'All admins see all' kept as intended | Revisit if you add teams/brokers
SEC-007 | Security | P1 | Deferred | Password-reset rate limit | Needs shared store | Set up Upstash Redis when ready
SEC-011 | Security | P1 | Deferred | Gemini per-user rate limit | Needs shared store | Set up Upstash Redis when ready
SEC-015 | Security | P2 | Deferred | daisyUI v3 outdated | Major upgrade, visual-regression risk | Approve + QA later
SEC-018 | Security | P2 | Deferred | Align Tailwind 3/4 | Major dep change | Approve + QA later
SEC-021 | Security | P2 | Deferred | Virus-scan uploads | Reduced by GAP-009 type limits | Pick a scanning service
SEC-023 | Security | P2 | Deferred | Activate endpoint lockout | Needs shared store | Set up Upstash Redis when ready
CMP-006 | Compliance | P1 | Deferred | CASL unsubscribe + postal address | Emails lack unsubscribe | Give me iClosed mailing address
ARC-007 | Architecture | P2 | Deferred | Mixed Tailwind 3+4 | Tied to SEC-018 | Approve + QA later
CMP-003 | Compliance | P0 | Not started | Gemini sub-processor DPA/disclosure | Legal + code | Sign DPA / disclose in privacy policy
GAP-001 | Gaps | P1 | Not started | Optimistic concurrency on deal edit | Last-write-wins | Migration + frontend conflict UI
GAP-002 | Gaps | P2 | Not started | Family-deal lookup race | No unique index guard | Migration + conflict handling
GAP-012 | Gaps | P2 | Not started | Resend retry / outbox |  | Needs outbox table + retry job
GAP-015 | Gaps | P2 | Not started | Bulk import file validation | Premise stale (CSV parsed client-side)
GAP-022 | Gaps | P2 | Not started | Zero automated tests |  | Greenfield test-suite setup
ARC-001 | Architecture | P1 | Not started | Pagination on /api/admin/deals | Whole table returned | Frontend + API
ARC-002 | Architecture | P1 | Not started | Unbounded listUsers loop (N+1) |  | Cache auth lookups
ARC-003 | Architecture | P2 | Not started | DealList virtualization | Needs pagination first
ARC-006 | Architecture | P2 | Not started | Pervasive any types |  | Repo-wide sweep
ARC-009 | Architecture | P2 | Not started | Consistent API error shape |  | ~84-route sweep (decision)
ARC-012 | Architecture | P2 | Not started | Test/release gate in CI | Largely covered by SEC-028 CI; tests=GAP-022